## Slide 1: Project Dashboard
Status Report

## Slide 2: Overview Projects (1/2)
Project
Project Sponsor
Started
Estimated
Duration
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue
Mobile Banking 2.0
Siron KYC / AML / Embargo
Processing Center Project
BPM Development
İnstant Payment Systems
Phase 1
NFC Payments
Business Continuity Plan
Corporate Internet Banking 2.0
Online Bank Account
İgor Okayev
????
????
????
????
????
Igor Okayev
Sattar Kazimov
Sattar Kazımov
Lala Hadjiyeva
Sevda Hajiyeva
Oleg Kucherov
Etibar Mammadov
Ramin Usubov
Sevda Hajiyeva
Sofya Dosayeva
Shahin Mirabutalubov
Samir Mustafayev
Nurlan Mammadli
Elchin Jabbarov
İgor Okayev

## Slide 3: Overview Projects (2/2)
Project
Project Sponsor
Started
Estimated
Duration
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue
Digital Branch
Marketplace
U’Loan (Payday) Project
İgor Okayev
Igor Okayev
????
Heybat Gadirov
Elchin Jabbarov
Sattar Kazimov
Zaur Aliyev

## Slide 4
Siron KYC / AML / Embargo Project Dashboard
Technology
KYC/AML/Embargo functionalities are ready for implementation/integration
Achievements
Risks
Igor Okayev
Lala Hajiyeva
Project Sponsor
Project Manager
????
Launch
Date
11 Feb 2019
Initiation
Date
Budget
Planned
2,000,000 AZN
Utilized
1,900,000 AZN
Estimated
200,000 AZN
Variance
(100,000 AZN)
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
22 (20) MH
20 MH
20 MH
76 (80) MH
2019
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2020
12
Milestones
Requirements collection and analysis
70%
Development
60%
Testing
20%
94%
Completed
Compliance department develops the requirements for the reporting milestone. To enable Embargo funcionality for incoming Swift payments, software has been purchased and is planned to be installed next week. KYC integration on Vabank awaits for the prioritization on IT Side.
Key Decisions
14 (20) MH
22 - Oct - 2020
Observations
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 5
Unibank Processing Center Project Dashboard
Technology
Achievements
Risks
Igor Okayev
Lala Hajiyeva
Project Sponsor
Project Manager
????
Launch
Date
17 Jan 2019
Initiation
Date
Budget
Planned
2,000,000 AZN
Utilized
1,900,000 AZN
Estimated
200,000 AZN
Variance
(100,000 AZN)
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
22 (20) MH
20 MH
20 MH
76 (80) MH
2019
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2020
12
Milestones
Requirements collection and analysis
70%
Development
60%
Testing
20%
Environment Preparation
Launch MVP (one ATM, POS)
Trainings
70%
Completed
Key Decisions
14 (20) MH
22 - Oct - 2020
Observations
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 6
NFC Payments (VTS Visa) Project Dashboard
Technology
Test Environment / Services
Achievements
Risks
Igor Okayev
Sevda Hajiyeva
Project Sponsor
Project Manager
23 Sep 2020
Launch
Date
08 Mar 2020
Initiation
Date
Budget
Planned
2,000,000 AZN
Utilized
1,900,000 AZN
Estimated
200,000 AZN
Variance
(100,000 AZN)
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
22 (20) MH
20 MH
20 MH
76 (80) MH
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Requirements collection and analysis
70%
Access VDC
60%
Solution Design
20%
Connectivity Configuration
Development
Testing
44%
Completed
Tasks related to Issuer Wallet & Garmin Pay are in progress.
Key Decisions
14 (20) MH
22 - Oct - 2020
Future deviations may occur / Visa is not certified on Millikart
Observations
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 7
NFC Payments (MDES MasterCard) Project Dashboard
Technology
Garmin Payment
Achievements
Risks
Igor Okayev
Sevda Hajiyeva
Project Sponsor
Project Manager
06 Oct 2020
Launch
Date
14 Jan 2020
Initiation
Date
Budget
Planned
2,000,000 AZN
Utilized
1,900,000 AZN
Estimated
200,000 AZN
Variance
(100,000 AZN)
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
22 (20) MH
20 MH
20 MH
76 (80) MH
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Requirements collection and analysis
70%
Access MDC
60%
Solution Design
20%
Connectivity Configuration
Development
Testing
40%
Completed
Tasks related to Issuer Wallet is in progress. NOTE: Project Plan is under development. Figures and milestones given above based on assumptions generated by similarities with VTS Project Plan.
Key Decisions
14 (20) MH
22 - Oct - 2020
Future deviations may occur / Visa is not certified on Millikart
Observations
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 8
BPM Development – Credit Module
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
Simplification of the process of issuing a loan at the branch. | A great amount of effort has been put into learning the process of working with ODM. | 
Further Steps/ Recommendations to the Project Steering Committee
Project Sponsor: | Farid Abushov | Project Manager: | Oleg Kucherov | Project start/ end dates | / 15.09.2020
Chart: Project Progress %
| Alkredit + Albali cross sale (15%) | Albali product (15%) | Alkredit with SMS (Without Cross Sale) (20%) | Loan Verification (20%) | Alkredit without SMS (Cross Sale) (30%)
Column2 | 0 | 0 | 0
Column3 | 0 | 0 | 0 | 0.8 | 0.99
Column4 | 10 | 16 | 19
40%
Completed

## Slide 9
BPM SPK
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
Working Products: Mədaxil & Konvertasiya Modulu. |  | 
Further Steps/ Recommendations to the Project Steering Committee
Analysis are being conducted to prioritize the implementation of Fast Money Transfer Systems in BPM.
Project Sponsor: | Farid Abushov | Project Manager: | Etibar Mammadov | Project start/ end dates | May 2019 / 15.09.2020
Chart: Project Progress %
| Fast Money Transfer Module | Receipts Module | Currency Conversion Module
Column2 | 0 | 0 | 0
Column3 | 0 | 0.9 | 1
Column4 | 19 | 21 | 28
%
Completed
Deadline for Unitransfer Sending

## Slide 10
Instant Payment Systems
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
Final Test Stage 1st of October – Go live (production) |  | 
Further Steps/ Recommendations to the Project Steering Committee
Project Sponsor: | Farid Abushov | Project Manager: | Ramin Usubov | Project start/ end dates | 01.08.2019 / 01.10.2020
Chart: Project Progress %
| Implementing Frontal C2B (POS) payment processing | ATM/Cash-in initiated Transfer | Retail Baranch initiated transfer - CRM | Retail Baranch initiated transfer - Vabank | İnternet Banking (corp) initiated transfer | Mobile Bank functionality development | Preparation of Back office clearing processes | Configuration of IPS connection and services via BUS
Column2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Column3 | 0.95 | 0 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 1
Column4 | 6 | 7 | 10 | 16 | 19 | 21 | 28
95%
Completed

## Slide 11
Business Continuity Plan
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
IT hardware's has been purchased / BCP is under development |  | 
Further Steps/ Recommendations to the Project Steering Committee
Project Sponsor: | Tural Hasanov | Project Manager: | Sofya Dosayeva / Shahin Mirabutalibov | Project start/ end dates | 04.05.2020/27.11.2020
Chart: Project Progress %
| Approval of the Executive Board | Procurement and Installation | Preparation and approval of BCP | Defining the source of financial and capital/asset requirements | Classification of the emergency cases and proposing action plan | Research of International Practice / study of similar legislation
Column2 | 0 | 0 | 0 | 0 | 0
Column3 | 0 | 0.5 | 0 | 0.1 | 0.3 | 1
Column4 | 0 | 10 | 16 | 19 | 28
40%
Completed

## Slide 12
Corporate Internet banking 2.0
Highlights/ Results | Deviations/ Issues | Budget Status
Business Requirements are being discussed with IT | Technical Limitations | 
Further Steps/ Recommendations to the Project Steering Committee
The business requirements of the project requires major architectural changes on IT systems. The first Sprint of the project has not officially started, project members are discussing the changes on Business Mobile Banking registration algorithms. After fixing the scope of project, detailed project plan will be created.
Project Sponsor: | Igor Okayev | Project Manager: | Samir Mustafayev / Nurlan Mammadli | Project start/ end dates | January 2020
Chart: 
| Sprint Review (5%) | Testing (15%) | Implementation (50%) | IT Analysis (5%) | Design (5%) | Business Specifications (20%)
Column2 | 0 | 0 | 0 | 0 | 0 | 0
Column3 | 0 | 0 | 0 | 0.7 | 0.8 | 0.9
Column4 | 7 | 10 | 16 | 19 | 21 | 28
0%
Completed

## Slide 13
Online Bank Account Opening – Individual Clients
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
Technical Documents / Mockup designs are ready | Approval of Compliance / Fatca Regulations | 
Further Steps/ Recommendations to the Project Steering Committee
Getting approvals on technical document from RM, Business, Information Security and Compliance departments are in process. Main uncertainty about the project is the law, that prohibits signing FATCA in an online format. Ministry of Economy has not taken the restrictions yet on this particular issue.
Project Sponsor: | Igor Okayev | Project Manager: | Sattar Kazimov | Project start/ end dates | February 2020
Chart: Project Progress %
| Approval & Closing (5%) | Testing (15%) | Implementation (50%) | Internal Approvals (5%) | Design (5%) | Business Specifications (20%)
Column2 | 0 | 0 | 0 | 0 | 0 | 0
Column3 | 0 | 0 | 0 | 0.5 | 1 | 1
Column4 | 7 | 10 | 16 | 19 | 21 | 28
0 %
Completed

## Slide 14
Digital Branch
Project Dashboard
Highlights/ Results | Deviations/ Reasons | Budget Status
ATM Functionalities Technical Documentation and Mock up designs |  | 
Further Steps/ Recommendations to the Project Steering Committee
Front End Vendor selection & prioritization process is on progress.
Project Sponsor: | Farid Abuşov | Project Manager: | Heybat Gadirov / Elchin Jabbarov | Project start/ end dates | February 2020
Chart: Project Progress %
| Test launch (10%) | İntegration Development (20%) | Front end business specification Development (30%) | Front end vendor selection and certification (10%) | Business functionality design (20%) | ATM Vendor Selection and Certification (10%)
Column2 | 0 | 0 | 0 | 0 | 0
Column3 | 0 | 0 | 0 | 0.3 | 0.6 | 1
Column4 | 10 | 16 | 19 | 21 | 28
10%
Completed