## Slide 1: Project Dashboard
Status Report

## Slide 2: Transformation Office
TO Key Mandate
  Develop Strategy and alignment functions’ strategy with overall Bank strategy
  Design TOM and drive change management
  Develop Project Governance and implement it across the Bank
  Bind Bank Key Resources and Assets together in cross-functional way to achieve goals
  Initiatives assessment from various perspectives
Strategy Planning and Execution
Operating Model Design
Projects Management (On Hold)
Process Management (On Hold)
Customer Journey Mapping (On Hold)
Innovation and Incubation (On Hold)
Governance and Change Management

## Slide 3: Change Management Governance Transformation Office
Governance Principles Design
Implementing Governance within New Project Portfolio
Implementing Bank wide Governance
A
B
C
A1
Design templates
A2
Alignment of templates within TO
A3
Alignment of templates within ExCom
B1
Data Collection from Project
Owners
B2
Data Verification & Development of Charters
B3
Start Capability Development Trainings
C1
PM Tool Implementation
C2
Driving whole projects portfolio
C3
Finalize Capability Development Trainings
B3
Driving new projects portfolio, support old project portfolio

## Slide 4: Overview Old Projects Portfolio (1/2)
Project
Project Sponsor
Started
Estimated
Delivery
Date
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue
Mobile Banking 2.0
Siron KYC / AML / Embargo
Processing Center Project
BPM Development - Credit
İnstant Payment Systems
Phase 1
NFC Payments
Business Continuity Plan
Corporate Internet Banking 2.0
Online Bank Account
İgor Okayev
Faig Huseynov
Faig Huseynov
Farid Abushov
Igor Okayev
Tural Hasanov
Igor Okayev
Sattar Kazimov
Sattar Kazımov
Lala Hadjiyeva
Sevda Hajiyeva
Oleg Kucherov
Heybat Gadirov
Ramin Usubov
Sevda Hajiyeva
Sofya Dosayeva
Shahin Mirabutalubov
Samir Mustafayev
Nurlan Mammadli
Elchin Jabbarov
İgor Okayev
August 2019
October2020
May
2020
December
2020
October2019
May
2020
February2019
May
2020
January
2019
January
2021
December
2019
January
2020
January
2021
February
2020
Hardware installment in Mingacevir is done and configuration of systems is underway.
IT implementation just begun.
Post-launch assessment is not performed
Post-launch assessment is not performed
Development of reporting module need high priority
Couldn’t receive information due to fact that neither plan nor any planning is done

## Slide 5: Overview Old Projects Portfolio (2/2)
Project
Project Sponsor
Started
Estimated
Duration
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue
Digital Branch
Marketplace
U’Loan (Payday) Project
İgor Okayev
Igor Okayev
Sattar Kazimov
Heybat Gadirov
Elchin Jabbarov
Sattar Kazimov
Zaur Aliyev
Business case/Financial Model have been presented, waiting for comments from stakeholders
Pre-project stage
February
2020

## Slide 6: Overview New Projects Portfolio
Project
Project Sponsor
Started
Estimated
Duration
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue
Strategy & Business Planning
U-Transform Initiative
U-Talent Initiative
Cost Optimization (ID)
Risk Management Module (TA consult)
Farid Abushov
Faig Huseynov
Faig Huseynov
TBD
Sevda Aliyeva
Heybat Gadirov
Natalya Sandler
Tural Hasanov
Farid Abushov
MVP delivery to be postponed to the end of March’21
Detailed Product Description, Analysis by IT, Brand Identity, ATM UX/UI design
Planning stage to be delivered by the end of Nov
TBD
Kick off date - 23.12.20; 3-6 months
Expected kick off date - 26.12.20; 1st phase duration
Sep’20
Sep’20
Nov’20
Nov’20
Dec’22
Dec’21
Dec’21
Aug’21
Apr’21
Apr’21

## Slide 7: Project Delivery Calendar 2020
January 20’
February 20’
March 20’
April 20’
May 20’
June 20’
July 20’
August 20’
September 20’
October 20’
November 20’
December 20’
Prestij Launch
Garmin Launch
Online Business Card
Western Union
Parking
Albali
POS

## Slide 8: Project Delivery Calendar 2021
January 21’
February 21’
March 21’
April 21’
May 21’
June 21’
July 21’
August 21’
September 21’
October 21’
November 21’
December 21’
Processing Launch
NFC
UCard

## Slide 9
Siron KYC / AML / Embargo Project Dashboard
Technology
AML/KYC/Embago systems operates in production environment
Achievements
Igor Okayev
Lala Hajiyeva
Project Sponsor
Project Manager
May 2020
Est. Delivery
Date
11 Feb 2019
Initiation
Date
2019
8
9
10
11
7
12
2
3
4
5
6
7
1
2020
2
3
4
5
1
6
Milestones
Requirements collection and analysis
100%
Development Siron KYC AML
60%
FUİ Reports
0%
Development Siron Embargo
Training
100%
100%
Key Decisions
22 - Oct - 2020
Observations
Embargo system has been integrated to SWIFT system. After automation internal processes, AZIPS will also be integrated to Embargo module.
Taking to account that systems have been successfully deployed, PM cannot close the project due to absence of FUI reports. Development of the reports should be done by internal IT resources, priority is necessary for pushing this topic forward
MMX reports will be implemented with the help of Unibank IT Resources. This task has not yet been prioritized.
Notes
70%
Completion Rate
8
9
10
11
12
2019
8
9
10
11
7
12
2
3
4
5
6
7
1
2020
2
3
4
5
1
6

## Slide 10
Unibank Processing Center Project Dashboard
Technology
Achievements
Igor Okayev
Sevda Hajiyeva
Project Sponsor
Project Manager
Planning to migrate to new Processing TX at 15.01.2021
Notes
Milestones
Requirements collection and analysis
Development
Testing
Environment Preparation
Launch MVP (one ATM, POS)
Trainings
Key Decisions
22 - Oct - 2020
Observations
8
9
10
11
12
2019
8
9
10
11
7
12
2
3
4
5
6
7
1
2020
2
3
4
5
1
6
100%
90%
75%
100%
100%
70%
Migration
60%
15 Jan 2021
Est. Delivery
Date
17 Jan 2019
Initiation
Date
75%
Completion Rate

## Slide 11
NFC Payments (VTS Visa) Project Dashboard
DIGITAL
Achievements
Igor Okayev
Sevda Hajiyeva
Project Sponsor
Project Manager
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Requirements collection and analysis
100%
H2H MilliKart
100%
Solution Design
70%
Testing
Development
Key Decisions
22 - Oct - 2020
Observations
Solution Design is preparing now. Once it is ready will go on creation connection with MilliKart and Testing full functionality
Notes
Going to Life
25%
TBD
Est. Delivery
Date
08 Mar 2020
Initiation
Date
55%
Completion Rate
2
3
4
5
6

## Slide 12
NFC Payments (MDES MasterCard) Project Dashboard
Digital
Successfully finished testing of MDES for Merchant and Garmin pay. Near to close finishing testing of Issuer Wallet.
Achievements
Igor Okayev
Sevda Hajiyeva
Project Sponsor
Project Manager
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Testing MDES for Merchant
100%
Testing Issuer Wallet
Testing GARMIN
Key Decisions
22 - Oct - 2020
Observations
Going to Life will be after successfully migration to TX solution. Planned to migrate to TX at 15.01.2021
Notes
50%
70%
15 Jan 2021
Est. Delivery
Date
14 Jan 2020
Initiation
Date
65%
Completion Rate
1
2
3
4
5
2022

## Slide 13
BPM Development Credit Module Project Dashboard
COMMERCIAL
Alkredit process without SMS
Alkredit + SMS
Achievements
Farid Abushov
Oleg Kucherov
Project Sponsor
Project Manager
Milestones
Pre-Design Stage
Alkredit process without SMS
BPM Interface/Front end
Testing
Alkredit + SMS
Key Decisions
22 - Oct - 2020
Observations
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
1
2021
2
3
4
5
1
6
100%
100%
100%
100%
100%
The next stage of implementation is the transfer of the online lending process to BPM.
Notes
12
19’
Albali card issuing
%
OAK Module
%
TBD
Est. Delivery
Date
December 2019
Initiation
Date
80%
Completion Rate

## Slide 14
BPM Development SPK Module Project Dashboard
TECHNOLOGY
Faster implementation of SPK transactions
Eliminating differences or errors that may arise between the SPK system and the Bank's internal systems
Achievements
Igor Okayev
Nigar Garibova
Project Sponsor
Project Manager
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Contact receipt
85%
Contact send
30%
Key Decisions
22 - Oct - 2020
Process improvement – became faster and easier to work with system
Negotiations continue with Western Union for integrations
Observations
Retail business:
BPM sisteminin imkanları ilə tanışlıq və tələblərin müəyyən edilməsi
Contact qəbul- Ekran formasının hazırlanması
Texniki tapşırığın hazırlanması
Çəkilmiş TO BE prosesə baxıb münasibət bildirmək
Ediləcək əlavələrin Risk ilə razılaşdırılması
Development:
Sistem üzrə ineqrasiya imkanlarının araşdırılması və tələblərin müəyyən edilməsi
Qəbul üzrə servisin yazılması
Servisin BPM-də inteqrasiyası
an formasının hazırlanması
Müştəri axtarışı - ekran forması və validasiyası
Kalkulyator imkanı
ASAN/KYC İBRES/BPM
Qəbul üzrə axtarış
Çap sənədlərinin hazırlanması
Completed spk:
Contact receipt 20%
Notes
December 2020
Est. Delivery
Date
July 2020
Initiation
Date
40%
Completion Rate
1
2
3
4
5
2022

## Slide 15
Strategy and Business Planning Project Dashboard
STRATEGY
Outcome of the first mini strategic session
Active involvement of project stakeholders
Achievements
Risks
Farid Abushov
Sevda Aliyeva
Project Sponsor
Project Manager
Budget
Planned
12 920 EUR
Utilized
0 EUR
Estimated
12 920 EUR
Variance
12 920
Human Resources
Business Analyst
Project Manager
Project Coordinator
Project Assistant
Grand Total
516 MH
816 MH
306 MH
2046 MH
2020 (MVP)
10
11
12
1
9
2
4
5
6
7
8
9
10
11
12
1
3
2021
2
2022
Milestones
Analysis of the market and the situation in the bank
30%
Development of a top-level strategy
10%
0%
Detailed strategy, long-term business plan and implementation plan
%
%
%
Key Decisions
408 MH
22 - Oct - 2020
To prolong the timeline of the project MVP phase to the end of March.
Observations
Analytical Function
Maturity Level
COVID-19
Market with High Convergency Rate
3
4
5
6
7
December 2021
Est. Delivery
Date
October 2020
Initiation
Date
20%
Completion Rate

## Slide 16
Strategy & Business Planning project
Project Charter
Project name |  | Project Purpose | Main Deliverables
Program Chief Customer | Transformation Committee | Enhancement of Corporate Governance by applying best practices in strategic & business planning Increase the effectiveness of strategy execution process (Strategy & Budget Committee, quarterly business reviews etc.) Development of strategic planning and execution related competencies of main stakeholders Establishment of internal Center of Expertise to facilitate and run annual Strategy Planning process (including AOP, objectives cascading etc.) | Corporate Governance & integrated approach to strategic planning & management Dynamic financial model, realistic roadmaps & effective process of monitoring Integration with performance management system Strategy Planning Toolkit Strategy Planning Trainings (main stakeholders, project team)
Project Sponsor | Farid Abushov |  | 
Project Manager | Sevda Aliyeva |  | 
Project Coordinator | Samir Hasanov |  | 
Main Stakeholders | FIN, C-level, Directors |  | 
Selected Vendor | TA Consult/ EBRD |  | 
Expected Start Date | September’ 2020 |  | 
Budget: | Risks: | Dependencies:
Proposed Total Budget: 99 338 Euro | Unpredictable market situation and as a result low-quality outputs of the 1st phase (moderate) | Involvement and commitment of C-level and Directors are success critical for the project implementation
Budget to be paid by UniBank: 12 920 Euro |  | 
Tentative Plan
 | 2020 (MVP) |  |  |  | 2021 (full-stack process) |  |  |  |  |  |  |  |  |  |  | 
Project Phases/ Milestones | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1. Analysis of the market and the situation in the bank |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
2. Development of a top-level strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Detailed strategy, long-term business plan and implementation plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 17
U_Talent Program (HR Functional Strategy Implementation)
Program name |  | Program Purpose/ Aspirations | Main Deliverables/ KPIs
Program Chief Customer | Executive Committee | Apply Best Talent Management Practices & Improve Employee Experience Institutionalize HR change management capabilities & competencies | To become one of top 5 employers in banking (based on Employer Brand Survey 2022) Increased Employee Engagement Index Decrease HiPo & Key contributors turnover
Program Sponsor | Faig Huseynov |  | 
Program Manager | Natalya Sandler |  | 
Main Stakeholders | All Leaders/ All Employees |  | 
Selected Vendor | Multi-vendor |  | 
Expected Start Date | October’ 2020 |  | 
Budget: | Risks: | Dependencies:
Total Budget: TBD | Budget constraints (high) Heavy Run agenda and operational load of UniBank leaders | Trust & Commitment of Top Team and all leaders of the bank
Tentative Scope/
Plan
 |  | 2020 |  |  | 2021 |  |  |  | 2022 |  |  | 
Projects/ Streams | Project Leaders | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Employer Brand Enhancement (acquisition, on-boarding etc.) | Gunel G/ Nurana M |  |  |  |  |  |  |  |  |  |  | 
2. Job Evaluation & Total Reward Standards | Natalya S/ Shahla M |  |  |  |  |  |  |  |  |  |  | 
3. Performance Management System implementation | Natalya S/ Viktoriya H |  |  |  |  |  |  |  |  |  |  | 
4. Leadership Development & Succession planning | Natalya S/ Sevda A |  |  |  |  |  |  |  |  |  |  | 
5. Corporate Culture & Employee Engagement | Natalya S/ Viktoriya H |  |  |  |  |  |  |  |  |  |  | 
6. Institutional Development of HR Function | Sevda A/ Natalya S |  |  |  |  |  |  |  |  |  |  | 
7. Automation of HR processes (transactional/transformational) | Natalya S |  |  |  |  |  |  |  |  |  |  | 

## Slide 18
U-TALENT PROGRAM (HR Functional Strategy Implementation)
Institutional development & corporate culture
- HR reorganization (OD & HR BPs
- Job Evaluation process started
- Top Team Development (Neuromap)
Achievements
Risks
Faig Huseynov
Natalya Sandler
Program Sponsor
Program Manager
Budget
Planned Total * -
4,028,500 AZN
(1,769,500 AZN for
2021 only)
Human Resources
(planning stage is still ongoing)
CTO
HRD
HR Project Managers/ Members
TO Partner
Grand Total
X MH
Y MH
Y MH
Z MH
2020
9
10
11
12
8
1
3
4
5
6
7
8
9
10
11
12
2
2021
1
Milestones
Employer Brand Enhancement
Job Evaluation & Total Reward
Performance Management System
Leadership Development & Succession
Corporate Culture Transformation
Institutional Development
Key Decisions
22 - Oct - 2020
- Detailed Project Plan is to be finalized by Mid-Dec’20
-PM process to be initiated in April after Strategy MVP
- Corp Culture project will start after ID project interview stage is finalized
Observations
Quality of planning
Turnover of Key HR
personnel
Lack of Leadership
(heavy run agenda)
HR Automation
5%
5%
15%
2022
X MH
Budget constraints
* excluding salary
harmonization
budget
December 2022
Est. Delivery
Date
Aug 2020
Initiation
Date
5%
Completion Rate
2
3
4
5

## Slide 19
U_Transform Initiative
Project name |  | Program Purpose | Main Deliverables/ KPIs
Program Chief Customer | Executive Committee | Reposition UniBank by changing products UVPs and enhancing Brand Communication Revamp Unibank Corporate Culture | Increased Brand Perception & NPS Increased Market share for the selected products/segments Increased Revenue per client/ ticket ratios Higher Employee Engagement in touch points Decreased turnover of HiPos & key contributors
Program Sponsor | Faig Huseynov |  | 
Program Manager | Heybat Gadirov |  | 
Main Stakeholders | Retail, Digital, IT, HR |  | 
Selected Vendor | Multiple-Vendor |  | 
Start Date | August’2020 |  | 
Budget: | Risks: | Dependencies:
Total Budget: TBD | Budget constraints (high) Unpredictable external market conditions | Cooperation and synergy between Retail, Digital and IT are success critical for the project
Tentative Scope/
Plan
 |  | 2020 |  |  |  |  | 2021 |  |  |  | 2022 |  |  | 
Projects/ Streams | Stream Leaders | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1. Brand Guidelines & Integrated Launch Campaign | Rasim B/ Sevda A |  |  |  |  |  |  |  |  |  |  |  |  | 
2. Hitting the market in key areas: Card/ Loan | Araz S/ Emil M |  |  |  |  |  |  |  |  |  |  |  |  | 
3. Hitting the market in key areas: BPM/ Loan process | Araz S/ Oleg K |  |  |  |  |  |  |  |  |  |  |  |  | 
4. Hitting the market in key areas: ATM & Mobile App integration | Sattar K/ Farid M |  |  |  |  |  |  |  |  |  |  |  |  | 
5. Revamp Unibank Corporate Culture (HiPo & Touch points) | Mikayil M/ Natalya S |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 20
U-TRANSFORM PROGRAM (Repositioning)
Grow in Core Business
Logo Renewal
U-card Product Description & IT feedback
U-card Design agency brief
ATM UX/UI design
Achievements
Risks
Faig Huseynov
Heybat Gadirov
Program Sponsor
Program Manager
Budget
Planned Total * -
3,708,339 AZN)
(2,740,339 AZN for
2021 only)
Human Resources
(planning stage is still ongoing)
Chief Retail Officer
Project Managers
IT/ Digital/ Marketing
TO Partner
Grand Total
X MH
Y MH
Y MH
Z MH
2020
9
10
11
12
8
1
3
4
5
6
7
8
9
10
11
12
2
2021
1
Milestones
Brand Guidelines & Integrated Launch Campaign
U-Card/ Loan
BPM/ Loan process
ATM & Mobile App Integration
Corporate Culture
(HiPos & Touch Points)
Key Decisions
22 - Oct - 2020
Detailed Roadmap of Key activities/ tasks is needed
We suggest to cover last item by U-Talent Program
SME/ micro dimensions to be added to the program???
Observations
Quality of planning
Turnover of Key
Contributors (incl. IT)
Lack of Leadership
(heavy run agenda)
10%
2022
X MH
Budget constraints
* excluding ATM/
digital branch design/
production
10%
to be covered in BPM project
10%
April 2021
Est. Delivery
Date
Aug 2020
Initiation
Date
<10%
Completion Rate

## Slide 21
Risk management enhancement project
Project Charter
Project name |  | Project Purpose | Main Deliverables of Phase 1
Project Sponsor | Farid Abushov | To enhance Risk Management Capabilities of the Group (UniBank & UniCapital) Review organizational structure including roles & responsibilities, authority maps etc. Streamline Group Risk Management processes | The recommendations for the regulations (including roles & responsibilities) and compositions of the Committees The recommendations for the system of authorities delegation The recommendations for products and limits systems, business processes etc.
Project Manager | Tural Hasanov |  | 
Project Coordinator | Samir Hasanov or Vafa Abdullayeva |  | 
Main Stakeholders | RM, Business Lines, HR, Legal, Corporate Secretary |  | 
Selected Vendor | TA Consult |  | 
Expected Start Date | October’ 2020 |  | 
Budget: | Risks: | Dependencies:
Proposed Total Budget: 147 100Euro | Project full stop after phase 1 (if we don’t agree on the phase 2 scope) Resource insufficiency by the bank | Involvement and commitment of working group (Risk function + Business lines) are success critical for the project
Budget to be paid by UniBank: 19 123Euro |  | 
Tentative Plan
2020 |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
Project Phases/ Milestones |  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 Organizational structure review and recommendations for TOM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1.2 UniCapital sub module (structure, framework, processes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
scope of the 2nd phase (UniBank) and all further steps will be defined upon the completion of the 1st phase

## Slide 22: Prioritization Approach Strategic Projects
 | Small | Medium | Large | Extra Large
High | High | High | Medium | Medium
Medium | Medium | Medium | Low | Low
Low | Medium | Low | Low | Low
Capacity Requirement
Project Prioritization Framework
Demand (Business Value)
Information Gathering & Analysis
Business Value Working Group
Delivery Team Capacity
Level of Effort
Valuation
Defined Score
Populates
Populates
Prioritized
Project Backlog
Low Priority High Priority
Continuous Value Measurement
Release Cycles
Sprint 1…x
Sprint x…y
Sprint y…z
Executive Committee
Project to Product
Backlogs
MVP 1
MVP 2
MVP 3
MVP 1
MVP 2
MVP 3
MVP 1
MVP 2
Sprint 1…a
Sprint a…b
Sprint b…c
Sprint 1…l
Sprint l…m
Product A
Product B
Product C
Risks
Populates

## Slide 23: Overview Strategic Projects
Project
Project Sponsor
Started
Estimated
Duration
Status
Project Manager
Comments
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Mitigated Risk/Issue
Unmitigated Risk/Issue

## Slide 24
Mobile Banking v2.0 Project Passport: Overview
Technology
Lorem ipsum dolor sit amet, consectetur adipiscing elit. Donec sit amet nisl vel turpis pharetra interdum. Quisque mollis nisl non elit luctus, ut maximus mi hendrerit. Ut luctus, est viverra venenatis facilisis, nibh arcu interdum metus, in vestibulum metus tellus dapibus purus. Nunc sed congue libero.
Project definition
Transfer and payment data
Cards data
Finance data
Risk data
Transfer and payment
Out of Scope
IT
Finance
HR
Risk
External Vendor
Key business stakeholders
Business Value / Success Factors
Type of project
Technology

Commercial
Supportive
Other
In Scope
Igor Okayev
Sattar Kazimov
Project Sponsor
Project Manager
20 Jan 2021
Launch
Date
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
20 MH
20 MH
20 MH
20 MH
80 MH
20 Jan 2020
Initiation
Date
Risks
Budget
Planned
2,000,000 AZN
CAPEX
1,800,000 AZN
OPEX
200,000 AZN
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 25
Mobile Banking v2.0 Project Passport: Timeline
Technology
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Requirements collection and analysis
Key Activities
Development
Testing
2
4
5
1
6
8
7
9
12
11
13
10
14
3
Sprint 1
Sprint 2
Sprint 3 and 4

## Slide 26
Mobile Banking v2.0 Project Dashboard
Technology
Achievements
Risks
Igor Okayev
Sattar Kazimov
Project Sponsor
Project Manager
20 Jan 2021
Launch
Date
20 Jan 2020
Initiation
Date
Budget
Planned
2,000,000 AZN
Utilized
1,900,000 AZN
Estimated
200,000 AZN
Variance
(100,000 AZN)
Human Resources
Business Analyst
Software Engineer
Product Owner
SRE Engineer
Grand Total
22 (20) MH
20 MH
20 MH
76 (80) MH
2020
8
9
10
11
7
12
2
3
4
5
6
7
8
9
10
11
1
2021
12
Milestones
Requirements collection and analysis
70%
Development
60%
Testing
20%
50%
Completed
Key Decisions
14 (20) MH
22 - Oct - 2020
Observations
Technology Risk 1
Operational Risk 1
Resource Risk 1
Technology Risk 2
Technology Risk 3
Technology Risk 4

## Slide 27: Technology Status Review
Technology/Deep Dive
Initiatives
Started/Ongoing
Completed
Delay/Roadblock/
requires further alignment
Starting later
Issues
Risks
On track
Milestones
Deadline
Pre.
Status
Achievements & Risks in last 2 weeks
Tasks in 3 months
1
Cur.
Status
2
18-Dec-2004
1
3
18-Dec-2004
18-Dec-2004
4
18-Dec-2004
6
18-Dec-2004
18-Dec-2004
5
7
18-Dec-2004
8
18-Dec-2004
10
18-Dec-2004
9
18-Dec-2004
18-Dec-2004